IRS Building Delegations

Performance Work Statement 

2 March 2003

Technical Exhibit 6                  
Page 3

Technical Exhibit 6

REQUIRED SUBMITTALS AND REPORTS
I.
SUBMITTAL REQUIREMENTS

The Contractor  shall submit the following data, reports, schedules, plans, and items to the COTR for approval and/or action as applicable, no later than the dates specified (for each site).

A.
Within 15-days Phase-In Period:

1.   Provide detailed resumes, certifications and licenses (Paragraph 3.5)
B.
Within thirty day Phase-In Period:

1. Buildings Operations Plan (Paragraph 3.1.1)

2. Quality Control Plan (Paragraph 3.11)
3. Proposed Water Treatment Program (Paragraph 3.2)

4. Initial Water Systems Analysis Report (Paragraph 3.2.1)

5. Existing Deficiency Report (Paragraph 3.10.2)

6. Contact Telephone Numbers for Contractor  (Paragraph 3.5.1)

7. Update all CMMS software/database records including the building equipment inventory and preventive maintenance schedule (Paragraph 3.4.2.A) (60 Days)  

8. Annual Preventive Maintenance Schedule (Paragraph 3.4)

9. Outage Preventive Maintenance Schedule Paragraph (3.4.2.B) 

10. Complete Water treatment Plan (Paragraph 3.2.1)

11. New Preventive Maintenance Guide Cards developed by the contractor  based on Manufacturer’s criteria (Paragraph 3.4.2.C and D)

12. Refrigerant Management Plan (Paragraph 3.9.5.1.1) (20 Days)
B. Thirty  (30) calendar days prior to contract expiration

1. Final Inspection Report (3.10.7.2)

C. Seven (7) calendar days prior to contract expiration:

1. Return Government Issued Manuals & Bulletins (Paragraph 5.1.3)

2. Update all CMMS and building systems databases (Paragraph 3.4 and 3.17)

3. Provide updated Refrigerant records to the Government (Paragraph 3.9.5)

D. Upon Final Expiration of the contract, or termination of employment, the Contractor shall return to the Government the following:

1. Identification/Building Badges issued to Contractor  and employees (Paragraph 3.8)

2. All keys/key cards (Paragraph 5.1.1)

3. All software and hardware and database information related to any Government Furnished or building systems 
4. Government furnished materials and equipment (Paragraphs 5.2 and 5.3)

II.
RECURRING REPORT/SUBMITTALS REQUIREMENTS.  

The Contractor shall provide the Government with all reports and submittals listed below.  In addition, the contractor shall provide any other reports required by the Government during the term of the contract.  The reporting format shall be as directed by the IRS Contracting Officer and or COTR.

	Report Description
	Due Date

	1.  Major equipment/systems not operational (Paragraph 3.1.10)
	Daily, as required, by 9:00 A.M. to COTR

	2.  Completed service call documentation returned to Government (Paragraph 3.3.9)
	Daily, within 24 hours of completion of Service Call work

	3.  Completed PM work order documentation in the CMMS and hard copy in Monthly Progress report (Paragraph 3.4.4)
	Daily, within 7 days of completion of PM work and Monthly Progress Report

	4.  COTR notification of work requiring opening or dismantling of equipment (Paragraph 3.10.2)
	Daily, as required before work is started

	5.  Asbestos Program Managers notification of work involving disturbing asbestos (Paragraph 3.9.8.1)
	Immediate notification prior to commencement of work.

	6.  Chiller Operating Logs (Paragraph 3.1.4) 
	Upon COTR request

	7.  Boiler Operating Logs (Paragraph 3.1.4)
	Upon COTR request

	8.  PM Accomplishments Report (Paragraph 3.14)
	3 work Weekly and monthly PM progress report.  A complete summary of all PM accomplishments in Monthly Progress Report

	9.  Inspection records, Quality Control Inspections (Paragraph 3.11.3)
	15-Days following inspection 

	10.  Water Analysis Report (Paragraph 3.2.2)
	Monthly, 5 calendar days after each test and summarized as part of the Monthly Progress Report.

	11.  Report of IDIQ Work Received and Completed (Paragraph 4.7)
	Monthly Progress Report

	12.  Status of all Open IDIQ Work (Paragraph 4.7) 
	Monthly Progress Report

	13.  Service Call Summary (Paragraph 3.14)
	Monthly Progress Report

	14.  Equipment History Report (Paragraph 3.1.10)
	Monthly Progress Report 

	15.  Refrigerant log (Paragraph 3.9.5.1.3)
	Monthly Progress Report



	16.  Equipment Check Logs (Paragraph 3.1.4)
	Monthly Progress Report

	17.  Utility Usage Report, electrical, fuel, etc. (Paragraph 3.1.9)
	Monthly, within three work days after reading meters 

	18.  Update Building Equipment Inventory in CMMS system (Paragraph 3.4.2)
	Annually (within the first 30 days of each option period) or as required by the COTR.

	19.  Employee documentation for new and replacement employees (Paragraph 3.5)
	As Required, 21 calendar days prior to the employees start date

	20.  Completion of Certified Testing such as elevators, infra red scans, etc. (Paragraph 3.4.6)
	As required, within 30 days of completion 

	21.  Reports of electrical distribution systems inspections, tests, PM, defects, etc. (Paragraph 3.4.6, 3.4.8)
	As required, initially before work starts and certified reports within 30 calendar days after completion of work

	22.  MFG PM guides for equipment not covered by current IRS guide (Paragraph 3.4.2)
	As required or as directed by the COTR

	23.  Changes in contact telephone numbers for key personnel (Paragraph 3.5.1)
	As Required when changes occur

	24.  Employee licenses/certifications replacement employees (Paragraph 3.5.1)
	As required but within 21 days of employee start date

	25.  Scheduled outages of critical systems for PM (Paragraph 3.19.2)
	As required 90 days in advance of scheduled outage

	26.  Scheduled Outage Plan (Paragraph 3.19.2) 
	As required 90 days in advance of scheduled outage

	27.  SF 295 and SF 295 Reporting (Subcontracting Plan)
	April 30 and October 30


NOTE:  All monthly reports shall be consolidated into a single Activity Report that shall be submitted by the 5th work day of the month following performance.

1
SOURCE SENSITIVE UNTIL RELEASE
Solicitation # TIRNO-09-R-00018

