## Open Issues
Tax Year 2025 Production Known Issues and Solution
IRIS A2A ATS
2026-08-03
Date entered | Form Type | Issue Type | Description of the Problem | Solution(s) | Projected Resolution Date
2026-08-03 | N/A | JWT | Some IRIS Application-to-Application (A2A) transmitters may receive an authentication error “System.Exception: (ESRV306) invalid client - The given JWT for client authentication is invalid” when generating JSON Web Tokens (JWTs) for client authentication. The error can occur when the JWT exp (expiration) claim is generated using a time zone-naive date/time value. In these cases, the expiration time may be interpreted as already expired during validation, causing the authentication request to fail. | Update the JWT expiration (exp) generation logic to use a UTC-based, time zone-aware date/time type to ensure the expiration time is calculated correctly in UTC. | N/A
2026-07-15 | CF/SF Forms | Business Rules | Business rules SHAREDIRFORM020, If CFSF Election State Code has a value, then CFSF Election Indicator in Submission Header must equal a value of "1" and SHAREDIRFORM022, If CFSF Election State Code has a value, then at least one Form Total By State Group must be present are flagging when present in the schema. | TBD | TBD
2026-07-15 | All Forms | Error Code and Error Description | The acknowledgement is not populating the business rule error code or error description. Instead the acknowledgement contains a generic error description. | TBD | TBD
2026-07-15 | All Forms | Acknowledgement missing RID | The acknowledgement does not populate the Recipient Id (RID) when requested using the Unique Transmission Identifier (UTID) | TBD. To obtain the RID, filers will need to call the IRIS help desk or use the Chatbot. | TBD
2026-03-03 | 1042-S | Schema validation | The 1042-S schema currently incorrectly requires an EIN on Line 15a if an intermediary or flow through entity is listed on the form. | TBD. Work Round: Entering an EIN of all zeros (00-0000000) will avoid the schema validation error until a fix is in place. | January 2027

## Resolved
Tax Year 2025 Production Known Issues and Solutions
IRIS A2A
Updated 8/3/2026
Date entered | Form Type | Issue Type | Description of the Problem | Solution(s) | Date Resolved
2025-12-03 | All | Acknowledgements | IRIS A2A ATS is not returning test acknowledgements which includes the status when processing is complete | A fix was deployed on 12/7/2025. | 2025-12-07
2025-11-25 | 1099-R | Missing Distribution Codes | The Distribution code combinations of SJ or JS are not being accepted. | The 1099-R schema was updated. | 2025-12-31