## Open Issues
Tax Year 2024 Production Known Issues and Solution
Taxpayer Portal
2025-03-17
Date entered | Form Type | Issue Type | Description of the Problem | Solution(s)
2025-01-07 | 1099-MISC | CSV File | The Form 1099-MISC CSV template is populating the wrong fields in the Taxpayer Portal system. Work around - When a user uploads 2025 1099-MISC forms via the CSV upload function and there are incorrect entries in the Form Account, FATCA Filing Requirements, and/or the 2nd TIN Notice, the user should review and confirm the info on the "Unsubmitted Forms" page or via the "Review Form Information" page on the CSV upload. To edit these entries the user can select the "Unsubmitted Forms" tile on the dashboard. Then using the "Group" Filter they can select the Upload date to help find affected forms. Click the "Ready to Submit" link for the file on the table. Then Select "Edit" link under the "Recipient Information" or the "Recipient Information" bread crumb link at the top of the page and correct the desired field. | Estimated fix date 01/11/2026

## Resolved
Tax Year 2024 Production Known Issues and Solutions
IRIS Taxpayer Portal
Updated 3/17/2025
Date entered | Form Type | Issue Type | Description of the Problem | Solution(s) | Date Resolved
2026-01-06 | 1099-R | Data entry | 1099R download in the Taxpayer Portal is generating a 2024 version of Part B for tax year 2025. | A Fix was deployed on 1/06/2026. | 2026-01-06
3/13/2025 | 1098 | Zip Code Entry | Box 8, Address or description of property securing mortgage, the manual entry of the address securing the mortgage is not allowing zip codes that start with zero. | A Fix was deployed on 3/17/2025. | 2025-03-17
2025-01-30 | 1098-F | Data entry | Box 9, Code, accepts only 1 code when there may be multiple applicable codes. If multiple codes are included in column AS on the CSV file, these must be removed in order to submit the file. | Programming will be updated.Estimated date of fix 2/24/2025. | 2025-02-24
2025-02-11 | 1098-Q | Date Entry | Box 1b, Annuity Start date, is only allowing a date within the current tax year to be entered. | Programming will be updated.Estimated date of fix 2/24/2025. | 2025-02-24
2025-02-11 | 1099-LTC | Date Entry | Box 5, Date Certified, is only allowing a date within the current tax year to be entered. | Programming will be updated.Estimated date of fix 2/24/2025. | 2025-02-24
2025-02-11 | 3921 | Date Entry | Box 1, Date Option Granted, is only allowing a date within the current tax year to be entered. | Programming will be updated.Estimated date of fix 2/24/2025. | 2025-02-24
2025-02-11 | 3922 | Date Entry | Box 1, Date Option Granted, is only allowing a date within the current tax year to be entered. | Programming will be updated.Estimated date of fix 2/24/2025. | 2025-02-24
2024-11-20 | 5498 | Data Entry | For TY 2024, Box 14a and 14b added repayment amounts and codes for: -EP (emergency personal expense) -DA (domestic abuse victim) -TI (terminally ill individual) These codes will not be available when IRIS opens in January for TY24/PY25 Taxpayer Portal will not allow the new codes at this time. On the Payments Page, it will not be present in the dropdown. For CSV upload, the user will receive an error message if those codes are used. | New repayment codes were added to the Taxpayer Portal for Box 14a and 14b. | 2025-02-10
2025-01-27 | All | Corrections | Taxpayer Portal Correct button is grayed out once a Receipt ID is successfully corrected. Any subsequent correction is disallowed. | A fix was deployed to allow corrections to be submitted on prior corrections. | 2025-02-10
2025-01-27 | All | Replacements | Taxpayer Portal Correct button is grayed out once a Receipt ID is successfully replaced. Any subsequent correction is disallowed. | A fix was deployed to allow corrections on replacements. | 2025-02-10
2025-01-27 | 1099-NEC | CSV Upload | Template is completed and uploaded but when the start button is selected it does not go to the "Review Form Information" page. The Taxpayer portal is not returning Form Level Errors for 1099-NEC CSV upload files that are incorrectly formatted or missing data elements. | A fix was deployed to show CSV file errors when templates are uploaded to the Taxpayer Portal. Using the 1099-NEC template Formatting Guidelines verify each column and field are completed as instructed. Required fields are marked with an asterisk "*" and checkboxes must contain a "Y" for checked/yes or "N" for unchecked/no. | 2025-02-10
2025-01-27 | 1099-NEC | CSV Upload | Template is completed and uploaded; once the start button is selected there is a "loading" page that doesn't progress. *This is unrelated to the start button issue listed January 27, 2025 on the "Current Issues" tab. | Verify if the forms are showing on the "Unsubmitted Forms" page. If showing, review information and select "Submit". If not showing, try to upload again. If the problem continues, please contact the help desk. | 2025-01-27
2026-01-06 | 1099-R | Data Entry | The Taxpayer Portal is incorrectly requiring both fields to contain an entry in Box 7, Distribution Code. Not all distributions will need an entry in both fields. | A fix was implemented to correct the issue. Filers are able to submit forms with only one entry in Box 7. | 2025-01-20
2025-01-13 | 1098 | Data Entry | Box 3, Mortgage Origination Date, is required to be the same year as the tax year being filed. Any year should be allowed. | A fix was implemented to correct the issue. Filers are not able to enter a prior year in Box 3. | 2025-01-20
2025-01-13 | 1099-PATR | CSV File | Box 12, Other Credit and Deductions, amounts are not being transferred from the CSV file to the Taxpayer Portal correctly. | A fix was implemented to correct the issue. The Taxpayer Portal is not transferring the data into the correct boxes. | 2025-01-20
2025-01-13 | PDF Downloads | PDF not downloading | PDF downloads are not being sent to the Notifications page. | Filers will need to redownload their PDF documents. | 2025-01-14
2025-01-13 | All form types | Schema Validation Rejections | Transmissions are rejected in the Taxpayer Portal but no reason is provided for the rejection when the filer selects the link under the "Transmission Status" column on the Submitted Forms page. Filers are able to see the error message if they download the Acknowledgement. The error message includes the following text: must be multiple of 0.01. | Resubmit the transmission as an original file. | 2025-01-13